| PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCYSERVICES-FOR SUBMISSION TO TREASURY, PPDA and PUBLICATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Procuring and Disposing Entity: |  |  |  |  | SHEEMA DISTRICT LOCAL GOVERNMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Financial Year: 2024-2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/No |  |  | Subject of procurement | Currency |  |  |  |  |  | Estimated cost |  |  |  | Source of funding |  |  | Procurement method |  |  |  | Contract Type |  |  | Pre-Qualification On (Yesorno) |  |  |  |  | ApplyReservationScheme(Yes/No) |  |  |  |  |  | INVITATIONANDAWARDOFBIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract signing date |  |  |  |  |  | Completion date |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Bid invitation date |  |  |  |  |  |  | Bid closing /Opening date |  |  |  |  | Approval evaluative report date |  |  |  |  | Award notification date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | Renovation of classrooms in 5 Primary Schools of Kagazi, Bunura, Nyakashoga, Rweibare and Kyeibanga Integrated |  |  |  |  |  |  | UGX |  |  |  | 159,286,179 |  | Program Conditional Grant-Non wage |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 |  | Completion of 7 Primary Schools –Kasaana 1, Kashekuro Model P/S ,Nyakanyinya, Rutoma Full Gosipel, Kyabahija Kyabuharambo P/S and Rwengiri P/S |  |  |  |  |  |  | UGX |  |  |  | 91,000,000 |  | Program Conditional Grant |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 |  | Construction of 8 stance VIP latrine at Nyakwebundika P/s |  |  |  |  |  |  | UGX |  |  |  | 45,000,000 |  | Program Conditional Grant |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 |  | Completion of 2 classroom block at Matsya P/S |  |  |  |  |  |  | UGX |  |  |  | 52,285,391 |  | Program Conditional Grant |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 5 |  | Construction of two classroom block at St Jude P/S |  |  |  |  |  |  | UGX |  |  |  | 65,725,670 |  | SFG |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 6 |  | Procurement of ICT Equipment for Ryakasinga CHE |  |  |  |  |  |  | UGX |  |  |  | 165,000,000 |  | UGIFT |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 7 |  | Procurement of Science Kits for Ryakasinga CHE |  |  |  |  |  |  | UGX |  |  |  | 56,047,000 |  | UGIFT |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 8 |  | Procurement of office stationery |  |  |  |  |  |  | UGX |  |  |  | 2,000,000 |  | None wage |  |  | Open Bidding |  |  |  | Frame work contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 8 |  | Repair and maintenance of Vehicles and motorcycle |  |  |  |  |  |  | UGX |  |  |  | 18,000,000 |  | None wage |  |  | Open Bidding |  |  |  | Frame work contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 9 |  | Construction of Ryakasinga Seed School |  |  |  |  |  |  |  |  |  |  | 496,113,909 |  | UGIFT |  |  | Open Bidding |  |  |  | Admeasurement Contract |  |  | Yes |  |  |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| HEALTH DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | Construction of 4 in one staff house at Bugongi H C III |  |  |  |  |  | UGX |  |  | 43,659,279 |  |  |  | PHC DEV’T |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 |  | Construction of 5 stance lined VIP Latrine at Shuuku H C IV |  |  |  |  |  | UGX |  |  | 20,000,000 |  |  |  | PHC DEV’T |  |  | Request for Quotation |  |  |  | Admeasurement Contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 |  | Procurement of Medical equipment to Kyeihara HC III |  |  |  |  |  | UGX |  |  | 150,000,000 |  |  |  | PHC DEV’T |  |  | Request for Quotation |  |  |  | Lumpsum contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 |  | Procurement of Medical equipment to Mabaare HC III |  |  |  |  |  | UGX |  |  | 150,000,000 |  |  |  | PHC DEV’T |  |  | Request for Quotation |  |  |  | Lumpsum contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 5 |  | Supply of fuel |  |  |  |  |  | UGX |  |  | 26,835,348 |  |  |  | PHC DEV’T |  |  | Open Bidding |  |  |  | Frame work contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 6 |  | Supply of stationery |  |  |  |  |  | UGX |  |  | 2,000,000 |  |  |  | PHC DEV’T |  |  | Open Bidding |  |  |  | Frame work contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 7 |  | Repair of departmental Vehicles |  |  |  |  |  | UGX |  |  | 6,000,000 |  |  |  | PHC DEV’T |  |  | Open Bidding |  |  |  | Frame work contract |  |  |  |  | Yes |  |  | No |  |  | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| PLANNING DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | construction of 8 stance with urinal ground lined pit latrine at Nyakambu P/S |  |  |  |  | UGX |  |  |  |  | 45,000,000 |  |  |  | DDEG |  |  |  | Request for Quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Renovation of RDCs office |  |  |  |  | UGX |  |  |  |  | 15,000,000 |  |  |  | DDEG |  |  |  | Request for Quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Construction of Administration block at the district headquarters |  |  |  |  | UGX |  |  |  |  | 21,163,563 |  |  |  | DDEG |  |  |  | Request for Quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Supply of stationery |  |  |  |  | UGX |  |  |  |  | 4,000,000 |  |  |  | DDEG |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Supply fuel |  |  |  |  | UGX |  |  |  |  | 21,863,766 |  |  |  | DDEG |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | procurement of a laptop |  |  |  |  | UGX |  |  |  |  | 2,500,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Lumpsum |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 7 | procurement of a photocopier for council |  |  |  |  | UGX |  |  |  |  | 4,500,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Lumpsum |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 8 | Telecommunications |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Lumpsum |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| PRODUCTION DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of Fuel |  |  |  |  | UGX |  |  |  |  | 104,110,326 |  |  |  | PMG/AEG/SSI |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of Stationery |  |  |  |  | UGX |  |  |  |  | 3,500,000 |  |  |  | PMG/AEG/SSI |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of computer |  |  |  |  | UGX |  |  |  |  | 4,000,000 |  |  |  | PMG/AEG/SSI |  |  |  | Micro Procurement |  |  | Lumpsum |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Supply of Agricultural supplies |  |  |  |  | UGX |  |  |  |  | 1,000,000 |  |  |  | LR |  |  |  | Micro Procurement |  |  | Lumpsum |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Rehabilitation of one acre of banana |  |  |  |  | UGX |  |  |  |  | 6,000,000 |  |  |  | PMG DEVT |  |  |  | Micro Procurement |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | Construction of pig sty structure |  |  |  |  | UGX |  |  |  |  | 39,060,000 |  |  |  | AEG DEVT |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 7 | Installation of small scale irrigation equipment |  |  |  |  | UGX |  |  |  |  | 178,217,164 |  |  |  | AEG |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | No |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 8 | Establishment of one acre of coffee |  |  |  |  | UGX |  |  |  |  | 6,338,227 |  |  |  | AEG DEVT |  |  |  | Micro Procurement |  |  | Admeasurement Contract |  |  |  | Yes |  |  |  | Yes |  | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| WATER SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Construction of rain water harvesting system at Bigona p/s in Rugarama s/c and Kyeibanga Primary school in Kitagata Sub county |  |  |  |  |  | UGX |  |  |  |  | 60,00,000 |  |  |  | DWSCDG |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Extension of Nshongi piped water to Bwayegamba in Kigarama Sub County |  |  |  |  |  | UGX |  |  |  |  | 90,000,000 |  |  |  | DWSCDG |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Extension of Bwehundu piped water to Kajju in Kigarama Sub County |  |  |  |  |  | UGX |  |  |  |  | 186,000,000 |  |  |  | DWSCDG |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Rehabilitation of Kyeihara Rain Water Harvesting Tank, Construction of 3 protected springs in Rugarama S/C and Rehabilitation of 3 protected springs |  |  |  |  |  | UGX |  |  |  |  | 52,000,000 |  |  |  | DWSCDG |  |  |  | Request for quotation |  |  | Admeasurement Contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Collection of Water Sample for 30 Old Sources and carrying out tests on every source, and carrying out water quality testing for 6 new sources |  |  |  |  |  | UGX |  |  |  |  | 8,200,000 |  |  |  | DWSCDG |  |  |  | Request for quotation |  |  | Lumpsum contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Procurement of fuel and lubricants for office operations |  |  |  |  |  | UGX |  |  |  |  | 3,330,000 |  |  |  | DWSCDG |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | Operation & Maintenance of office computers, photocopier and printers |  |  |  |  |  | UGX |  |  |  |  | 1,600,000 |  |  |  | DWSCDG |  |  |  | Micro Procurement |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 7 | Procurement of office stationery |  |  |  |  |  | UGX |  |  |  |  | 1,600,000 |  |  |  | DWSCDG |  |  |  | Micro Procurement |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 8 | Operation and maintenance of office vehicle and motorcycle |  |  |  |  |  | UGX |  |  |  |  | 7,500,000 |  |  |  | DWSCDG |  |  |  | Open Bidding |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| WORKS (ROADS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of fuel, Murram and concrete culverts for light Grading of Kasaana –Kyeihara road in Kasaana S/C (7km) |  |  |  |  |  | UGX |  |  |  |  | 83,799,296 |  |  |  | URF |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of fuel, Murram and concrete culverts for maintenance of Kyarwera-Kasaana road in Kasaana S/C (8km) |  |  |  |  |  | UGX |  |  |  |  | 89,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of fuel, Murram and concrete culverts for maintenance of Kyarwera –Kishabya and a spur from Bagashes home to Kirundo in Shuuku S/C (7km) road |  |  |  |  |  | UGX |  |  |  |  | 136,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Supply of fuel, Murram and concrete culverts for maintenance of Migiina-Rwengiri-Buringo in Kigarama S/C 10km road |  |  |  |  |  | UGX |  |  |  |  | 235,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | Supply of fuel and Murram for maintenance of Muziira-Kitakure-Migyerebiri- Matsyoro in Kyangyenyi S/C 10km |  |  |  |  |  | UGX |  |  |  |  | 60,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 7 | Supply of fuel, Murram, and concrete culvert for maintenance of Buraro-Kanuuka in Kitagata T/C 4km road |  |  |  |  |  | UGX |  |  |  |  | 64,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 8 | Supply of fuel and Murram swamp filing of Orujeebe swamp along Nyakabiriizi –Kyeibanga road |  |  |  |  |  | UGX |  |  |  |  | 137,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 9 | Supply of fuel, murram and concrete culverts for maintenance of Nyakambu-Nyabwiina-Kangore in Masheruka S/C 10km |  |  |  |  |  | UGX |  |  |  |  | 99,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 10 | Supply of fuel, murram and culverts for maintenance of Kamurinda-Kakindo Kalyango in Kitagata T/C 14km |  |  |  |  |  | UGX |  |  |  |  | 98,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 11 | Supply of fuel, murram and concrete culverts for maintenance of Nyakarama –Bigona-Irashagye in Rugarama 6km |  |  |  |  |  | UGX |  |  |  |  | 126,000,000 |  |  |  | PDG |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 12 | Supply and installation of culverts at Masheruka SS approach |  |  |  |  |  | UGX |  |  |  |  | 8,000,000 |  |  |  | URF |  |  |  | Micro procurement |  |  | Admeasurement contract |  |  |  | Yes |  |  | Yes | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 13 | Repair and maintenance of heavy machines and department vehicle |  |  |  |  |  | UGX |  |  |  |  | 241,527,819 |  |  |  | URF |  |  |  | Open bidding |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 14 | Supply of fuel for Office Operations |  |  |  |  |  | UGX |  |  |  |  | 50,858,346 |  |  |  | URF |  |  |  | Open bidding |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 13 | Supply of fuel for district roads committee |  |  |  |  |  | UGX |  |  |  |  | 16,000,000 |  |  |  | PDG/URF |  |  |  | Force Account Mechanism |  |  | Admeasurement contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 14 | Supply of office stationery |  |  |  |  |  |  |  |  |  |  | 2,000,000 |  |  |  | URF |  |  |  | Open bidding |  |  | Frame work contract |  |  |  | Yes |  |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
|  | STATUTORY DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | provision of welfare services |  |  |  |  |  | UGX |  |  |  |  | 4,800,000 |  |  |  | LR |  |  |  | Bid Opening |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | supply of stationery for PDU and District Service Commission |  |  |  |  |  | UGX |  |  |  |  | 8,970,000 |  |  |  | LR |  |  |  | Bid Opening |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Repair of vehicles for District Chairperson |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | LR |  |  |  | Bid Opening |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Supply of small office equipments |  |  |  |  |  | UGX |  |  |  |  | 560,000 |  |  |  | LR |  |  |  | micro procurement |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Advertising services (District Service Commission and PDU) |  |  |  |  |  | UGX |  |  |  |  | 6,400,000 |  |  |  | LR |  |  |  | Bid Opening |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | supply of Fuel |  |  |  |  |  | UGX |  |  |  |  | 16,600,000 |  |  |  | LR |  |  |  | micro procurement |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| ADMINISTRATION DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Procurement of fuel and lubricants |  |  |  |  |  | UGX |  |  |  |  | 15,000,000 |  |  |  | Unconditional Grant |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Maintenance of vehicles |  |  |  |  |  | UGX |  |  |  |  | 10,000,000 |  |  |  | Unconditional Grant |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Procurement f stationery |  |  |  |  |  | UGX |  |  |  |  | 8,000,000 |  |  |  | Unconditional Grant |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Procurement of office equipment |  |  |  |  |  | UGX |  |  |  |  | 2,000,000 |  |  |  | Unconditional Grant |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| COMMUNITY BASED SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Purchase of office stationery |  |  |  |  |  | UGX |  |  |  |  | 2,110,000 |  |  |  | non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of meals and refreshment |  |  |  |  |  | UGX |  |  |  |  | 4,000,000 |  |  |  | Conditional Grant |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of fuel for office operations |  |  |  |  |  | UGX |  |  |  |  | 2,700,800 |  |  |  | Non Wage and LR |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| FINANCE DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of fuel |  |  |  |  |  | UGX |  |  |  |  | 30,000,000 |  |  |  | Non Wage and LR |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of stationery |  |  |  |  |  | UGX |  |  |  |  | 12,750,000 |  |  |  | Non Wage and LR |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of meals and welfare services |  |  |  |  |  | UGX |  |  |  |  | 2,600,000 |  |  |  | Non Wage and LR |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| TRADE AND INDUSTRY DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of fuel for office operations |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| DISTRICT SERVICE COMMISSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of fuel |  |  |  |  |  | UGX |  |  |  |  | 3,500,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of stationery |  |  |  |  |  | UGX |  |  |  |  | 1,200,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of meals and releshment |  |  |  |  |  | UGX |  |  |  |  | 2,770,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| SHUUKU TOWN COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Procurement of stationery |  |  |  |  |  | UGX |  |  |  |  | 2,770,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Procurement of fuel |  |  |  |  |  | UGX |  |  |  |  | 2,770,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | No |  | Yes | No |  |  |  |  |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  |
| 3 | Maintenance and servicing of motor vehicles |  |  |  |  |  | UGX |  |  |  |  | 2,770,000 |  |  |  | Non wage |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | No |  | Yes | No |  |  |  |  |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  |
| BUGONGI TOWN COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Renovation of CBS & Production offices and tiling Council hall |  |  |  |  |  | UGX |  |  |  |  | 6,500,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | Yes |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of Fuel for light grading 26km |  |  |  |  |  | UGX |  |  |  |  | 48,000,000 |  |  |  | URF |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of 12 pieces 900mm culverts |  |  |  |  |  | UGX |  |  |  |  | 15,000,000 |  |  |  | URF |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Fuel for council day to day operations including garbage collection |  |  |  |  |  | UGX |  |  |  |  | 8,000,000 |  |  |  | LR/UCG |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 5 | Routine mechanical maintenance of council trucks |  |  |  |  |  | UGX |  |  |  |  | 16,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 6 | Procurement of laptop for finance department |  |  |  |  |  | UGX |  |  |  |  | 1,300,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | Yes |  |  |  | 5/8/2024 |  |  |  |  |  |  | 16/8/2024 |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| KASAANA SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Procurement and installation of culverts |  |  |  |  |  | UGX |  |  |  |  | 6,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Construction of slaughter slab |  |  |  |  |  | UGX |  |  |  |  | 5,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| KIGARAMA SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of10,000 Ltr plastic water tank to Bwayegambya p/s |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of10,000 Ltr plastic water tank to Nyakashonga P/s |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| MASHERUKA SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Roofing of Administration Block at the Sub County headquarters |  |  |  |  |  | UGX |  |  |  |  | 2,000,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Supply of office stationery |  |  |  |  |  | UGX |  |  |  |  | 200,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| KITAGATA SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | purchase of a computer |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Lump sum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | supply, installation and construction of end structures for the reinforced pipe culvert |  |  |  |  |  | UGX |  |  |  |  | 7,894,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| KITAGATA TOWN COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply of assorted office stationery |  |  |  |  |  | UGX |  |  |  |  | 2,000,000 |  |  |  | LR |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Procurement of one laptop |  |  |  |  |  | UGX |  |  |  |  | 1,600,000 |  |  |  | DDEG |  |  |  | Micro procurement Bidding |  |  | framework contract |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Supply of fuel ,oils and lubricants for road works |  |  |  |  |  | UGX |  |  |  |  | 22,000,000 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Procurement and installation of culverts |  |  |  |  |  | UGX |  |  |  |  | 2,800,000 |  |  |  | Road fund |  |  |  | Micro procurement |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| KYANGYENYI SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Procurement of desks for 7 primary schools |  |  |  |  |  | UGX |  |  |  |  | 4,943,050 |  |  |  | DDEG |  |  |  | Micro procurement |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 2 | Procurement of desk top computer |  |  |  |  |  | UGX |  |  |  |  | 2,500,000 |  |  |  | DDEG |  |  |  | Micro procurement |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 3 | Construction of waste pit at Matsyoro HC II |  |  |  |  |  | UGX |  |  |  |  | 1,500,000 |  |  |  | LR |  |  |  | Micro procurement |  |  | framework contract |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| 4 | Mechanize of roads(Kyanemba-Ryamsa 2.5km,Kyakahungu I and ii -Kinyinya TC 2KM ,RUSHAMBYA-RYAKAHUNGU I 2.5KM |  |  |  |  |  | UGX |  |  |  |  | 14,166,120 |  |  |  | Road fund |  |  |  | Open Bidding |  |  | framework contract |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  | 10/12/2024 |  |  |  |  |  |
| RUGARAMA SUB COUNTY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Procurement and installation of rain water harvesting tank |  |  |  |  |  | UGX |  |  |  |  | 3,505,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 | Rehabilitation of slaughter slab |  |  |  |  |  | UGX |  |  |  |  | 1,500,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | Yes | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 | Procurement of fuel |  |  |  |  |  | UGX |  |  |  |  | 14,793,000 |  |  |  | Road fund |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 | Rehabilitation of monthly market at Kagati |  |  |  |  |  | UGX |  |  |  |  | 2,005,000 |  |  |  | LR |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| MASHERUKA TOWN COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Supply & installation of the gate at mabare HC III |  |  |  |  |  | UGX |  |  |  |  | 2,000,000 |  |  |  | PHC |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 | Supply of fuel |  |  |  |  |  | UGX |  |  |  |  | 28,00,000 |  |  |  | Road fund |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 | Supply and installation of culverts |  |  |  |  |  | UGX |  |  |  |  | 9,000,000 |  |  |  | Road fund |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 | Supply of 3 twin seater desks to Masheruka modern pls. |  |  |  |  |  | UGX |  |  |  |  | 4,000,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 5 | Purchase of cupboard |  |  |  |  |  | UGX |  |  |  |  | 1,000,000 |  |  |  | DDEG |  |  |  | Micro Procurement |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 6 | Grading of Kabutsye-Katojo Nyakiborera-Mukono Kanyegangye Centre Business District 28km |  |  |  |  |  | UGX |  |  |  |  | 30,000,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| KAKINDO TOWN COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | processing of Town Council Land Title |  |  |  |  |  | UGX |  |  |  |  | 2,000,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 | stone pitching of CBD trenches in the Town Council |  |  |  |  |  | UGX |  |  |  |  | 3,752,747 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 | light grading of 5km Kamurinda-Kakindo road |  |  |  |  |  | UGX |  |  |  |  | 4,000,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 | light grading of 1.5km Rweibare play ground Tibazindwa Katooma road |  |  |  |  |  | UGX |  |  |  |  | 1,996,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 5 | light grading of 4.7 Kakindo Nyakabiriizi Kifunjo Bwiina road |  |  |  |  |  | UGX |  |  |  |  | 5,066,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 6 | light grading of 5km Kakindo Rweibare Mushanju road |  |  |  |  |  | UGX |  |  |  |  | 6,270,000 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 7 | light grading of 2km Rweibare s s Rukangiro Mugumya road |  |  |  |  |  | UGX |  |  |  |  | 2,708,385 |  |  |  | URF |  |  |  | Force Account |  |  | Admeasurement |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| DISPOSAL OF ABSOLETE ASSETS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Disposal of old Motorcycles |  |  |  |  |  | UGX |  |  |  |  | 600,000 |  |  |  | Local Revenue |  |  |  | Auctioning |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 2 | Disposal of old Vehicles |  |  |  |  |  | UGX |  |  |  |  | 8,000,000 |  |  |  | Local Revenue |  |  |  | Auctioning |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 3 | Disposal of milling machine |  |  |  |  |  | UGX |  |  |  |  | 2,800,000 |  |  |  | Local Revenue |  |  |  | Auctioning |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 4 | Disposal of scraps |  |  |  |  |  | UGX |  |  |  |  | 3,000,000 |  |  |  | Local Revenue |  |  |  | Auctioning |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 5 | Disposal of eucalyptus trees at Rukaragwe in Bugongi T/C |  |  |  |  |  | UGX |  |  |  |  | 8,000,000 |  |  |  | Local Revenue |  |  |  | Public Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 6 | Disposal of cows at Rubaare farm |  |  |  |  |  | UGX |  |  |  |  | 16,300,000 |  |  |  | Local Revenue |  |  |  | Public Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 7 | Disposal of old computers and type writer |  |  |  |  |  | UGX |  |  |  |  | 670,000 |  |  |  | Local Revenue |  |  |  | Auctioning |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 8 | Leasing of Rwanama Land |  |  |  |  |  | UGX |  |  |  |  | 5,070,000 |  |  |  | Local Revenue |  |  |  | Public Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
| 9 | Leasing of land at Nyanga- Kakunyu –Sheema Municipality |  |  |  |  |  | UGX |  |  |  |  |  |  |  |  | Local Revenue |  |  |  | Public Bidding |  |  | Lumpsum |  |  |  |  | Yes |  | No | 5/8/2024 |  |  |  |  |  |  |  | 16/8/2024 |  |  |  |  |  |  | 23/8/2024 |  |  |  |  | 5/9/2024 |  |  |  |  | 10/9/2024 |  |  |  |  |  | 10/12/2024 |  |  |  |  |
|  | Prepared by |  |  |  |  |  |  |  |  |  |  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Designati on: |  |  |  | Senior Procurement Officer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Approved by |  |  |  |  |  |  |  |  |  |  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Designati on: |  |  |  | Accounting Officer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |